## CPT Gallery module estimation
Estimation of performing Gallery module's critical path testing
Estimation by Test cases
Testing activities | Test case execution time (average), minutes | Test cases number | Assumed bugs found, % from test cases number | Assumed bugs found, number | Bug hunting and reporting time (average), minutes | Coefficients
Values | 5 | 45 | 20 | 9 | 7 | i. | Risk impact, % of total testing activities time | 15
[6 empty] | ii. | Number of runs (according to number of Browsers) | 3
Total time | 4.9 |  |  |  |  | Estimation result, hours:
Test cases execution, hours | 3.8
Bug hunting and reporting, hours | 1.1 |  |  |  |  | 14.4
Formula: Estimation result, hours =
(Test cases execution total time, hours * Number of runs + Bug hunting and reporting total time, hours) * (1+Risk impact / 100)

## Full app testing estimation
Estimation of performing BVF app full testing
Estimation by work breakdown
N | Activity | Time, hours | Coefficients
1. | Test Plan creation | 3 | i. | Risk impact, % of total testing activities time | 15
2. | Requirements review | 3.5 | ii. | Communication, % of total testing activities time | 20
3. | Team work organization | 2 | iii. | Number of runs (according to number of Browsers) | 3
Test cases creation |  |  | iv. | Testing team members | 7
| Test case creation (average), minutes | 7 | Estimation result, hours:
| Total test cases number | 490
4. | Total time for test-cases creation | 57.2 | 54.1
5. | Test cases review | 3.5
Test-cases execution
| Test case execution (average), minutes | 5
| Total test cases number | 490
6. | Total time for test-cases execution | 40.9
Bug hunting and reporting
| Assumed bugs found, % from test cases number | 20
| Assumed bugs found, number | 98
| Bug hunting and reporting time (average), minutes | 7
7. | Total amount for bug hunting and reporting | 11.5
8. | Test environment Setup | 7
9. | Build deployment (Installation testing) | 3.5
10. | TRR creation | 2
11. | Localization testing | 3.5
12. | GUI testing | 12
13. | Usability testing | 4
Total time |  | 153.6
a. | One-time activity | 93.2
b. | Time for the testing in each browser | 60.4
Total time adjusted for coefficients |  | 378.672
Formula:Total time adjusted for coefficients, hours =
(Time for the testing in each browser, hours * Number of runs + One-time activity, hours) * (1+Communication/100) * (1+Risk impact / 100)
Formula: Estimation result, hours =
Total time adjusted for coefficients / Testing team members